## Sprints
Sprint | Week | Sprint Goal | Start Date | End Date | Sprint State | Comments
1 | 2/3 | Start brain storming on what to do for the project and write it down in the srs | 2025-04-28 | 2025-05-09 | Inactive | Completed
2 | 4/5 | Finish up SRS including defining functions | 2025-05-12 | 2025-05-23 | Inactive | Completed
3 | 6 | Refinement of SRS ready for submission | 2025-05-26 | 2025-05-30 | Inactive | Completed
4 | 9 | 1.Write a function to display main menu and allow user to pick what login option they want(logged in, sign up or guest) 2.Write a function to allow user to key in and delete numbers from the keypad and store the correct value | 2025-06-16 | 2025-06-20 | Inactive | Completed
5 | 10 | 1.Write a function to hash a password 2.Write a function to check if password is correct 3.Create a database and create a table to store user data | 2025-06-23 | 2025-06-27 | Inactive | Completed
6 | 11 | 1.Write a function to allow user to Signup 2.Write a function to allow user to login | 2025-06-30 | 2025-07-04 | Inactive | SignUp function only finished till the part where if the function is ran with the correct parameters, the correct data will be stored in the database
7 | 12 | 1.Refine SRS 2.Generate Bar codes for product spmart is selling 3.Finish writing signup function 4.Start with web design | 2025-07-07 | 2025-07-11 | Inactive | Yining is starting on making the front end of the website. This can take a few weeks
8 | 13 | 1.Write a function to scan and read barcode of product 2.Write the main function for the scanning of items process including cancelling of item and viewing of cart 3.Implement stuff account information in database and link it to project 4.Continue with web design | 2025-07-14 | 2025-07-18 | Inactive | Part 2 seems difficult and probably will need to continue next week.
9 | 14 | 1.Continue with website development 2.Build scanning barcode function 3.Build overall buying procedure(try to complete this week) | 2025-07-21 | 2025-07-25 | Inactive | We realise that we needed to set up admin database, so the buying of items procedures were delayed. We try to finish it by this week. Website overall structure and main features are working and only needs tweaking( pick up qr code to work and add address when user chooses delivery)
10 | 15 | 1. Build overall checkout procedure(might take more than one week) 2. Create a release 3. Continue web building by adding more features | 2025-07-28 | 2025-08-01 | Inactive | We had a hard time dockerizing the application and so checkout function wasn’t complete. Website is mostly done, we are now trying to get the qr code for pick up to show relevant information when scanned.
11 | 16 | 1. Finished checkout function 2. integrate with website 3. dockerize whole project and make a release (basically the project needs to be done by this week and refinements to be done the following week) | 2025-08-04 | 2025-08-08 | Inactive | Docker is working and can now run both hardware and software. However, we realise some core feauters for website is still missing. Will implement it in the last week
12 | 17 | 1. Finish up website login, signup points system 2. Build the final docker image and push it into docker hub 3. Take demo video 4. Finish system test report 5. Refine SRS | 2025-08-11 | 2025-08-15 | Active | FINALLLLLL WEEEEKKKKKKK

## Active Sprint Board (hidden)
To Do | Doing | Done

## Product Backlog
ID | Story Title | Story Description | Definition of Done | Estimated Effort (hours) | Actual Effort (hours) | Status | Sprint
1 | Create Use Case Diagrams in SRS document | As a Software Developer, I need to define all the different Use Case Diagrams for the Automated Checkout System | All necessary Use Case Diagrams are defined in the SRS document SRS document is commited and pushed to Github | 4 | 5 | To Do | Sprint 1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95 | [5 empty] | Doing
96
97
98
99
100

## enum (hidden)
Sprint | Start Date | End Date | Story Status | Spint State
Sprint 1 |  |  | To Do | Inactive
Sprint 2 |  |  | Doing | Active
Sprint 3 |  |  | Done | Closed
Sprint 4
Sprint 5
Sprint 6